## Submission Requirements
SUBMISSION REQUIREMENTS
Week | Deliverables
1 | Project Charter
2 | LoFi Prototype
3 | Requirements Gathering
4 | Work Breakdown Structure (WBS)
5 | Communication Plan
6 | Test Plan (Yellow Boxes Only)
7 | High Fidelity (HiFi) Prototype
8 | Test Plan (Green Boxes)

## 1 - Project Charter
PROJECT CHARTER
Give a name for the project / prototype ---> | Project Name | PeaceBot – AI for Safer Digital Spaces
Group leader's name ---> | Project Manager | Lecia
Give a group name ---> | Team Name | Blank | Topic Selected | Peaceful or inclusive societies | <-- Select one topic from Annex A
| Team Members |  | Business Case
| Name | Role | PeaceBot is an AI-powered solution designed to foster safer and more respectful digital conversations. By utilizing NLP techniques such as Text Censoring , Conflict Prediction, and Cross-Language Communication, it aims to reduce online conflicts, promote empathy, and enhance global digital communication. This prototype addresses the growing concern of online toxicity and communication barriers, offering individuals, educators, and organizations an easy-to-use tool for promoting positive discourse in multilingual and multicultural environments. |  | <-- Describe in general: - What is the prototype? - What is the AI solution? e.g., Computer Vision / NLP - How it addresses the topic above
Group member's name and role --> Role could include developer, researcher, system integration, etc. Feel free to create new roles for your group members | Lecia | Project Manager
| Jeraldine | AI Developer
| Alina | UI/UX Designer
Fill in your answers in the yellow boxes

## 2 - LoFi Prototype
LOW FIDELITY (LoFi) PROTOTYPE
#VALUE!
This Lo-Fi prototype is a early design of the App; PeaceBot. It is an app to assist people to text others in a meaningful and contextual way, so people can understand what we're saying to them. It also provides assistance when writing some criticizing comments to make sure it is not hostile to the recipient. This app uses models from HuggingFace to provide kindness for messages and comments.
Feature 1 | Anonymous Reporting System | Feature 2 | Text Censoring | Feature 3 | Conflict Flag Forecaster | Feature 4 | Cross-Language Tone Coach
#VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | g
This feature will allow you to report another user who has committed a wrong action or when he/she cyberbullies you |  | This feature will censor harsh or swear words to prevent younger users from learning foul language until at a legal age |  | This feature will analyze if your comment is hostile or not with the flag as a guidance |  | This feature will translate and analyze your input to a different language, it will also modify the output so the recipient will know what you are talking about
Fill in your answers in the yellow boxes

## 3 - Requirements Gathering
REQUIREMENTS GATHERING
| Features | Security / Ethics Requirement | Hardware Requirement | Software Requirement
You may add more rows if needed ---> Ensure that the features listed is at least TRL3 and be realistically developed within the time frame | Anonymous Reporting System | Reports must be stored securely and kept anonymous | 4GB RAM server with SSD storage for fast access to reports.xlsx. | Use streamlit, pandas, and openpyxl to handle form input and Excel report saving.
| Text Censoring | Maintain transparency logs to prevent misuse or over-censorship and allow appeal for flagged messages. | Device must support real-time string comparison with 4GB RAM and local compute (CPU) for fuzzy matching text in real time. | Use rapidfuzz for fuzzy matching and regex (re) to censor offensive words.
| Conflict Flag Forecaster | The model must avoid profiling users and be trained on diverse datasets to prevent bias. | GPU-enabled machine (e.g., NVIDIA RTX 3060) for efficient model usage and sufficient memory to load toxicity models like unitary/toxic-bert. | Use HuggingFace transformers to run both sentiment and toxicity analysis pipelines.
| Cross-Language Tone Coach | Ensure translations are contextually accurate to prevent tone distortion across languages. | 8GB RAM system for loading multilingual models efficiently, GPU or stable internet connection for downloading multilingual models if needed. | Use MarianMTModel, MarianTokenizer, and langdetect to translate user messages.
Fill in your answers in the yellow boxes

## 4 - WBS
WORK BREAKDOWN STRUCTURE (HARDWARE) |  |  | WORK BREAKDOWN STRUCTURE (SOFTWARE)
1. Insert one task for each hardware resource identified in the "Requirements". |  |  | 1. Insert one task for each software resource identified in the "Requirements".
WBS Code | WBS Description | Resources Needed | WBS Code | WBS Description | Resources Needed
H1 | Development Machine |  | S1 | Anonymous Reporting System
| A personal laptop or desktop with minimum 8GB RAM, multi-core CPU (e.g., Intel i5/Ryzen 5) for smooth coding and testing. | Laptop/Desktop (8GB+ RAM, i5/Ryzen 5 or better) | S1.1 | Manages tabular report data and writes to Excel. | Excel
H2 | Local Storage |  | S2 | Text Censoring
| At least 1GB free space for storing reports (reports.xlsx), packages, and temporary model files | Internal SSD/HDD with 1GB+ available | S1.2 | Replace offensive words with asterisks. Using the library for fuzzy matching to detect variations of offensive words. | 1.RapidFuzz with threshold
H3 | Optional External Display |  | S3 | Implement Conflict Flag Forecaster
| An additional monitor can enhance development productivity, especially when working with Streamlit UI and code simultaneously. | 1080p Monitor, HDMI/VGA cable | S1.3 | Shows tone and score on the interface, uses a pre-trained model to detect toxicity/conflict potential. | Use unitary/toxic-bert model
H4 | Internet Connection |  | S4 | Create Cross-Language Tone Coach
| Stable broadband or Wi-Fi for accessing Hugging Face models, installing packages, and testing translations. | Broadband/Wi-Fi (minimum 10 Mbps recommended | S1.4 | Detects the language of user input and provides translation across supported languages (Chinese, Hindi). | 1. Use langdetect 2. Use MarianMT model
Fill in your answers in the yellow boxes |  |  | Fill in your answers in the yellow boxes

## 6 & 8 - Test Plan
HARDWARE TEST CASES
Case ID | Test Description | Test Designed By | Test Executed By | Test Date | Expected Results | Actual Results | Pass / Fail | Notes
HW-01 | Verify reports.xlsx can be created and written to | Lecia |  |  | Pass
HW-02 | Test model download and API loading via Hugging Face | Lecia |  |  | Pass
HW-03 | Ensure enough disk space for logs and Excel reports | Jeraldine |  |  | Pass
HW-04 | Ensure Hugging Face token (if used) is read securely | Jeraldine |  |  | Pass
SOFTWARE TEST CASES
Case ID | Test Description | Test Designed By | Test Executed By | Test Date | Expected Results | Actual Results | Pass / Fail | Notes
SW-01 | Check if known offensive words are detected and censored | Lecia |  |  | Pass
SW-02 | Validate tone classification using the NLP model | Lecia |  |  | Pass
SW-03 | Ensure reports are saved properly via the form | Jeraldine |  |  | Pass
SW-04 | Input simple messages and verify translated version matches expected meaning. | Jeraldine |  |  | Pass
INTEGRATION TEST CASES
Case ID | Test Description | Test Designed By | Test Executed By | Test Date | Expected Results | Actual Results | Pass / Fail | Notes
INT-01 | Check if censored messages are properly passed to translation | Lecia |  |  | Pass
INT-02 | Verify that flagged words are replaced with asterisks without breaking tone analysis or layout. | Lecia |  |  | Pass
INT-03 | Verify reports appear in admin panel after submission | Jeraldine |  |  | Pass
INT-04 | Ensure multilingual tone detection still works | Jeraldine |  |  | Pass
USER ACCEPTANCE TEST CASES
Case ID | Test Description | Test Designed By | Test Executed By | Test Date | Expected Results | Actual Results | Pass / Fail | Notes
UAT-01 | Verify users feel confident that their identity is not collected or exposed. | Lecia |  |  | Pass
UAT-02 | Ask users if they feel the tool successfully hides offensive content, even if exact words are hidden. | Lecia |  |  | Pass
UAT-03 | Confirm users feel the prediction is understandable and helpful in real communication. | Jeraldine |  |  | Pass
UAT-04 | Ask users if the translated message still feels appropriate in their native language. | Jeraldine |  |  | Pass
| Fill in your answers in the yellow boxes | To be supervised by Lecturer

## 5 - Communication Plan
COMMUNICATION PLAN
Person | Role | Communication Frequency | Format / Channel | Tasks
Lecia | Project Manager | Daily | Text | Manages the project plans, organizes, leads, and delivers a project successfully.
Jeraldine | AI Developer | Daily | Text | Creates smart programs that solve problems by learning from data.
Alina | UI/UX Designer | Daily | Text | Designs how apps and features look and feel to make them easy and enjoyable to use.
Fill in your answers in the yellow boxes

## 7 - HiFi Prototype
HIGH FIDELITY (HiFi) PROTOTYPE
#VALUE!
A high-fidelity prototype of PeaceBot was developed using Streamlit to closely replicate the final user interface and core functionalities. It includes full interaction workflows for all four features: Text Censoring, Conflict Flag Forecaster, Cross-Language Tone Coach, and the Anonymous Reporting System. The design simulates the actual system with functional backend logic, realistic responses, and live data handling (such as tone analysis, multilingual translation, and Excel logging). This allows users and stakeholders to experience the system's intended look and behavior as if it were fully deployed.
Feature 1 | Anonymous Reporting System | Feature 2 | Text Censoring | Feature 3 | Conflict Flag Forecaster | Feature 4 | Cross-Language Tone Coach
#VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE!
The Anonymous Reporting System allows users to discreetly report harmful or inappropriate communication without revealing their identity. Users can select a reason for the report, identify the subject, and optionally provide details. Submitted reports are securely stored in an Excel file and accessible only by administrators through a password-protected panel. This feature empowers users to flag problematic behavior in a safe and structured way, fostering a more respectful digital environment. |  | This feature automatically scans user input for offensive, abusive, or sensitive language using a blocklist combined with fuzzy matching. Any detected words are censored by replacing them with asterisks, and users are warned if inappropriate terms are found. This proactive filtering helps maintain respectful communication and prevents the spread of harmful content without completely silencing user input. |  | The Conflict Flag Forecaster analyzes the message for signs of toxicity using a pre-trained model. It classifies each message into three risk levels—low, moderate, or high—based on the severity of toxic language detected. Users receive immediate visual feedback so they can reflect and revise messages that may unintentionally escalate conflict. This feature is especially useful in sensitive discussions, helping maintain constructive communication. |  | This feature bridges communication gaps by detecting the language and emotional tone of user messages. It supports automatic translation into Hindi or Chinese while preserving the message’s tone and removing subtitle formatting tags for cleaner output. By helping users understand both how their message feels and how it may be perceived across languages, this feature promotes clearer, culturally sensitive interactions.
Fill in your answers in the yellow boxes

## Gantt Chart
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE | AIPD
PROJECT MANAGER | Lecia
COMPANY NAME | Peacebot
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Task 1 (Project Charter)
1.1 | Define Project Scope and Purpose | Lecia & Jeraldine | 2025-04-08 | 2025-04-12 | 4 | 100%
2 | Task 2 (Lo-fi)
2.1 | Designing lo-fi | Alina | 04/15/25 | 04/30/2025 | 15 | 100%
2 | Task 2 (Requirements Gathering)
2.1 | Identify Project Requirements | Lecia & Jeraldine | 2025-04-10 | 2025-04-15 | 5 | 100%
3 | Task 3 (Work Breakdown Structure)
3.1 | Structure Development Work | Lecia & Jeraldine | 2025-04-16 | 2025-04-22 | 6 | 100%
4 | Task 4 (Test Planning)
4.1 | Draft Testing Framework | Lecia & Jeraldine | 2025-04-17 | 2025-04-22 | 5 | 100%
5 | Task 5 (Prototype Development)
5.1 | Implement the AI Prototype | Lecia & Jeraldine | 2025-04-22 | 2025-05-24 | 32 | 100%
6 | Task 6 (Test Execution)
6.1 | Run Tests | Lecia & Jeraldine | 2025-05-24 | 2025-05-26 | 2 | 100%
7 | Task 7 (Final Presentation)
7.1 | Prepare Slides | Lecia, Jeraldine & Alina | 2025-05-26 | 2025-05-27 | 1 | 100%